## How To Use
BU SERVICES — 2026 CONFERENCE ACTION TRACKER · HOW TO USE THIS WORKBOOK
This workbook is the operational backbone of the BU Services 2026 conference programme. It works alongside the HTML Conference Action Plan portal. Read this sheet before making any changes.
📋 WORKBOOK OVERVIEW
Three tabs work together — each has a different purpose
| Tab 1 — Action Tracker | The main working list. 72 action items, one per row. Every conference task from booking flights to post-show Salesforce entry. Owners, due dates, status dropdowns, actual cost tracking, and reference numbers (ACT-001 to ACT-072). This is what the team updates week to week.
| Tab 2 — Dashboard | Auto-updates as you change statuses in the Action Tracker. Shows completion % by owner and by month. No manual entry needed — just change statuses in Tab 1 and this refreshes automatically.
| Tab 3 — Year Calendar | One row per conference — the full 2026 calendar view. Dates, locations, attendees, booth status, estimated cost, and the APPROVAL column. This is where Jon's approval decisions are recorded and where budget totals by approval status are calculated.
| Companion HTML Portal | The HTML Conference Action Plan file (open in Chrome) is the visual review layer. Use it to browse conferences, approve/reject in the browser, and export a summary. The Download buttons in the HTML deliver this Excel and the Budget Model directly.
✅ APPROVAL WORKFLOW — Step by Step
Jon reviews conferences in the HTML portal → decisions recorded here in Year Calendar tab → actions activate in Action Tracker
1 | Open the HTML Conference Action Plan in Chrome | File: BU_Services_Conference_Action_Plan.html. Open locally in Chrome or from SharePoint. The Approval Summary panel is at the very top below the header — it shows 0 approved until you start deciding.
2 | Review each conference card | Scroll to Section 03 — Conference Action Cards. Each card shows the conference details, strategic score, estimated cost, initiative alignment, and full action checklist. Filter by priority using the buttons at the top of the section.
3 | Click Approve / Hold / Reject on each card | Each card has a decision bar at the bottom. ✓ Approve = green border. ⏸ Hold = amber. ✗ Reject = card dims to 50% opacity. Add an optional note in the text field (e.g. 'Budget too high — reduce headcount' or 'Confirm waitlist first'). Decisions save automatically to browser localStorage — they persist if you close and reopen the file.
4 | Review the Approval Summary panel | The panel at the top of the HTML updates in real time: count of Approved / On Hold / Rejected / Pending, and four budget totals showing how much spend is committed, on hold, cut, or undecided.
5 | Export Approvals | Click the '📤 Export Approvals' button in the summary panel. A modal appears with a formatted text summary of all decisions. Click 'Copy to Clipboard'. This gives you the full list to share with Shanny and the commercial team.
6 | Update this Excel — Year Calendar tab → Column M | Open the Year Calendar tab. Find each conference. Change the dropdown in Column M (Approval Decision) to match your HTML decisions: Approved / On Hold / Rejected / Pending. The cell turns green/amber/red automatically. Add any notes in Column N. The four budget summary rows at the bottom update instantly.
7 | Action Tracker auto-reflects the decisions | The Action Tracker tab has a Column O (Conference Approval) which VLOOKUP pulls from the Year Calendar. Any conference marked Rejected will show 'Rejected' in red next to every related action item — Shanny and the team immediately know which logistics to cancel or not book.
📝 ACTION TRACKER — Column Guide
Tab 1 · 72 rows · one action per row
| A — Month | Which calendar month this action belongs to (Jan, Feb, Mar... or 'Ongoing' for standing items). Used by Dashboard to calculate monthly completion rates.
| B — Conference | Conference name. Links to Year Calendar via VLOOKUP for the approval status. 'ALL SHOWS' = applies to every conference (standing rules).
| C — Priority | HIGH / MED-H / MED / LOW — matches the conference priority rating from the strategic scoring model.
| D — Initiative | Which of the 5 BU Services initiatives this action serves: Mining NDT · Pipeline DA · Powerline · Nuclear/OPG · 3X Composite · All Initiatives.
| E — Owner | Person responsible for completing this action. Shanny Tremblay = all logistics. Commercial leads = account prep and Salesforce. Jon = strategic decisions.
| F — Category | Logistics (travel, hotels, freight, booth) · Commercial (account prep, Salesforce, messaging) · Admin (budget review, standing rules).
| G — Action Item | The specific task. Written as a clear instruction — not a vague goal. Each action has a single owner and a single deliverable.
| H — Due Date | Target completion date. Format: YYYY-MM-DD for sortable dates, or relative ('After each show', 'Monthly', 'Quarterly'). Sort this column to see what's coming up.
| I — Status | DROPDOWN — change this to track progress. Not Started (default/red) · In Progress (amber) · Complete (green) · Blocked (purple) · N/A (grey). The Dashboard tab reads this column for all completion metrics.
| J — Actual Cost | Enter real invoice amounts here as they come in (blue = input cell). Used by the running total at the bottom and by the quarterly budget vs actual review.
| K — Done ☐ | Manual checkbox column — tick ☑ when complete as a quick visual scan. Not formula-driven, just a convenience column for Shanny's weekly review.
| L — Completed Date | Enter the date when status is changed to Complete. Helps track whether actions were done on time vs late.
| M — Notes/Updates | Free text — add any context, blockers, confirmations, or follow-up notes here. Italicised grey text.
| N — Ref # | ACT-001 through ACT-072. Use these reference numbers when communicating about specific actions (e.g. 'ACT-014 is blocked — hotel sold out').
| O — Conf. Approval | Auto-populated via VLOOKUP from Year Calendar Col M. Shows the approval status of the parent conference — turns green/amber/red. If a conference is Rejected, all its action items show 'Rejected' here so Shanny knows to cancel bookings.
🔴🟡🟢 STATUS DROPDOWN GUIDE
| Not Started | Default state for all actions. Red text on red background. No work has begun.
| In Progress | Work has started but is not complete. Amber. Use this when flights are being searched, a hotel is being checked, or a prep deck is being drafted.
| Complete | Action fully done. Green. For logistics: booking confirmed + confirmation email received. For commercial: leads in Salesforce + tagged correctly.
| Blocked | Cannot proceed — waiting on something external (e.g. waitlist response, Jon decision, budget approval). Purple. Add a note in Col M explaining what is blocking it.
| N/A | Action does not apply — e.g. a booth-shipping action for a walkin-only conference. Grey. Better than deleting the row as it preserves the audit trail.
👤 WHO DOES WHAT — Owner Quick Reference
| Shanny Tremblay | Conference Logistics | All flight bookings, hotel reservations, badge registration, booth coordination, freight shipping. Highest action count. Start Jan–Mar bookings immediately.
| Éric Carmichael | IT / Systems | Power Automate flows, Salesforce field config, SharePoint Lists, OneNote structure, deck scheduling script. See Go-Live Roadmap for his full task list.
| Jon Eustace | CEO — Strategic | Approval decisions, strategic gap actions (Nuclear/Powerline gaps), ASNT booth sign-off, API consolidation call with Ekoscan BU.
| Olivier Marcotte | CRO — Nuclear/OPG | Pre-schedules OPG + Bruce Power meetings at CNA and IPEIA. Nuclear MSA strategy conversations. Largest initiative owner ($47.9M).
| Vinoth Tharma | Commercial Lead East | Mining NDT target lists at NDTMA, ECNDT, ASNT, CIM. Nuclear cross-sell. Attends 6 conferences — most commercial travel on the team.
| Max Aggrey | Commercial Lead West | IPEIA coordination lead. 3X Composite cross-sell kit. West coast mining at CIM Vancouver. IPC Pipeline prep.
| Rick Carlton | Pipeline DA Lead | Pipeline DA messaging consistency across 7 shows: PPIM → AMPP → IPEIA → API Insp. → IPC → IPCE → API Tank. Owns all Pipeline DA target lists.
| Mathieu Beauchesne | EVP | Powerline initiative at T&D Chicago + Cigre Paris. Owns Powerline gap identification (new Canadian utility show). Quarterly budget vs actual review.
| Alex Cyr | COO | Smart Energy Halifax walkin. Operational capacity planning.
| Louis-Pierre Théberge | Nuclear Specialist | CGSB certification status — confirm all team qualifications before CNA + IPEIA. OPG outage eligibility depends on this.
| Jeremy Irwin | Dir. Finance, EIG NA | Quarterly conference budget vs actual review alongside Jon and Mathieu. Finance oversight on actual spend vs Budget Model.
| All Attendees | Post-Show Rule | Every person attending any conference must enter all leads into Salesforce within 48 hours of return. BU_Initiative__c tag mandatory on every opportunity. No exceptions.
📏 RULES & CONVENTIONS
| 48-hour Salesforce rule | Non-negotiable. Every lead from every conference must be in Salesforce within 48 hours of returning. Tag BU_Initiative__c on every opportunity. This feeds the Sunday Power Automate flow → actuals.json → Command Centre. If it's not in Salesforce, it doesn't exist commercially.
| Blue cells = editable inputs | Throughout this workbook, blue text on a light blue background means the cell is an input you should change. Black text = formula. Do not overwrite black formula cells. If you need to correct a formula error, contact Éric.
| Actual cost column (J) | Enter real invoice or receipt amounts in Column J as they come in. Do not estimate — only real actuals. Estimates live in the Budget Model (separate file). This tracker records what was actually spent.
| Never delete rows | If an action no longer applies, change Status to N/A. Deleting rows breaks VLOOKUP references in the Dashboard and disrupts the reference number sequence (ACT-001 to ACT-072). Add new rows at the bottom if needed.
| Approval column (O) is read-only | Column O in the Action Tracker is formula-driven — it reads from the Year Calendar Col M. Do not type in Column O directly. To change an approval decision, go to Year Calendar → Col M dropdown.
| Quarterly review dates | Jon, Mathieu (EVP), and Jeremy Irwin (Dir. Finance) review actual vs budget four times per year: Q1 Apr 15 · Q2 Jul 15 · Q3 Oct 15 · Q4 Jan 15, 2027. Update Col J actuals before each review date.
| Ref numbers are permanent | ACT-001 through ACT-072 are fixed reference numbers. Use them in emails, Slack, and meeting notes to refer to specific actions (e.g. 'ACT-014 is blocked pending Jon decision'). Do not renumber.
💡 TIPS FOR GETTING THE MOST OUT OF THIS WORKBOOK
| → Sort Col H (Due Date) to see what's urgent | Click the dropdown arrow on the Due Date column header and sort A→Z. All upcoming deadlines float to the top. Do this every Monday morning for a weekly logistics check.
| → Filter Col E (Owner) for individual workload | Click the dropdown on Owner and select a single name — instantly see only that person's actions. Shanny can filter to her name to see just logistics tasks. Rick can filter to see his Pipeline DA prep list.
| → Filter Col I (Status) = Blocked to find problems | Filter Status = 'Blocked' to instantly see everything that is stuck and needs a decision or escalation. Review this in every commercial leadership meeting.
| → Filter Col O (Approval) = Rejected to cancel bookings | After Jon approves/rejects in the HTML portal and you update Year Calendar, filter Col O = Rejected. Every action for rejected conferences surfaces immediately — Shanny can cancel bookings in one session.
| → Use the Dashboard for meeting reporting | The Dashboard tab gives a clean summary by owner and by month. Screenshot it for the monthly commercial meeting to show conference preparation progress at a glance.
| → Keep the Budget Model open alongside this file | This tracker records actuals (Col J). The Budget Model (separate file) has the estimates and assumptions. Compare them side by side at quarterly reviews to understand where the model was accurate and where it needs calibrating.
BU Services Commercial Management System · 2026 Conference Action Tracker · Jon Eustace, CEO North America · Ekoscan Integrity Group · Confidential

## Action Tracker
Read this before using the tracker. Three roles. Each has a specific job. None overlap.
📋 SHANNY TREMBLAY — Conference Logistics |  |  |  |  | ✅ JON EUSTACE — Conference Approvals & SF Outcomes |  |  |  |  | 💰 JEREMY IRWIN — Budget vs Actual Review
Logistics Coordinator — BU Services (Nucleom/Nortech) ONLY |  |  |  |  | CEO North America — Strategic decisions + commercial outcomes |  |  |  |  | Director of Finance, EIG North America — Financial oversight
✔ After each BU Services conference: open this file on SharePoint |  |  |  |  | ✔ Review Conference Action Plan (HTML) → Approve / Hold / Reject each show |  |  |  |  | ✔ Quarterly budget vs actual review: Apr 15 · Jul 15 · Oct 15 · Jan 15
✔ Year Calendar tab → find conference row → enter total actual cost in Column S “Total Actual (CAD)” |  |  |  |  | ✔ After each conference: run SF report 'Conference Leads 2026' |  |  |  |  | ✔ Reviews Col J (cost breakdown) vs Col K (budget estimate) per conference
✔ Action Tracker tab → enter actual costs by category (Col J) for detail |  |  |  |  | ✔ Enter leads + opps counts via Teams Adaptive Card (sent automatically) |  |  |  |  | ✔ Flags any show exceeding budget by >15% — brief explanation required
✔ NOT responsible for Ekoscan BU shows (PPIM, NDTMA, AMPP, COFREND, API EIG) |  |  |  |  | ✔ This feeds Cost per Lead + Cost per Opp KPIs in the Command Centre |  |  |  |  | ✔ Reviews Salesforce outcomes (leads, opps) alongside cost data
⚠ ALL ATTENDEES — 48-HOUR SALESFORCE RULE: Enter all leads in Salesforce within 48 hours of returning. Tag BU_Initiative__c on every opportunity. No exceptions — the Sunday PA flow reads this data.
Month | Conference | Priority | Initiative | Owner | Category | Action Item | Due Date | Status | Actual Cost (CAD) | Done ? | Completed Date | Notes / Updates | Ref # | Conference Approval | Logistics Owner (BU)
Jan | PPIM 2026 | HIGH | Pipeline DA | Rick Carlton | Logistics | Confirm booth #113 details and freight shipping address with organizer | 2025-12-15 | Not Started |  | ☐ |  | Already booked | ACT-001 | Pending | Ekoscan BU
Jan | PPIM 2026 | HIGH | Pipeline DA | Ekoscan BU Logistics | Logistics | Book flights YQB→Houston (IAH) for Jeff, Anthony, Aaron | 2025-12-01 | Not Started |  | ☐ |  | Ekoscan BU manages logistics — coordinate only · Return ~$820/person CAD | ACT-002 | Pending | Ekoscan BU
Jan | PPIM 2026 | HIGH | Pipeline DA | Ekoscan BU Logistics | Logistics | Book hotel — Hilton Americas or nearby for 5 nights | 2025-12-01 | Not Started |  | ☐ |  | Ekoscan BU manages logistics — coordinate only · ~$295/night | ACT-003 | Pending | Ekoscan BU
Jan | PPIM 2026 | HIGH | Pipeline DA | Rick Carlton | Commercial | Prepare Pipeline DA talking points and target account list for Houston | 2025-12-20 | Not Started |  | ☐ |  | Align with Vinoth on messaging | ACT-004 | Pending | Ekoscan BU
Jan | PPIM 2026 | HIGH | Pipeline DA | Ekoscan BU Logistics | Logistics | Ship booth display and materials to George R. Brown Convention Center | 2026-01-10 | Not Started |  | ☐ |  | Ekoscan BU manages logistics — coordinate only · Allow 5 business days lead | ACT-005 | Pending | Ekoscan BU
Jan | PPIM 2026 | HIGH | Pipeline DA | Rick Carlton | Commercial | Schedule post-show debrief and enter leads into Salesforce within 48h of return | 2026-01-25 | Not Started |  | ☐ |  | Tag all opps with BU_Initiative__c = Pipeline | ACT-006 | Pending | Ekoscan BU
Feb | NDTMA 2026 | HIGH | Mining NDT | Vinoth Tharma | Commercial | Prepare TFM/PCI presentation — confirm with organizer abstract deadline | 2026-01-15 | Not Started |  | ☐ |  | Speaker slot confirmed | ACT-007 | Pending | Ekoscan BU
Feb | NDTMA 2026 | HIGH | Mining NDT | Ekoscan BU Logistics | Logistics | Book flights YQB→Las Vegas for Dillon, Jeff, Fred, Guillaume, Anthony | 2025-12-15 | Not Started |  | ☐ |  | Ekoscan BU manages logistics — coordinate only · Return ~$750/person CAD | ACT-008 | Approval Decision | Ekoscan BU
Feb | NDTMA 2026 | HIGH | Mining NDT | Ekoscan BU Logistics | Logistics | Book hotel — Golden Nugget, 4 nights | 2025-12-15 | Not Started |  | ☐ |  | Ekoscan BU manages logistics — coordinate only · ~$295/night | ACT-009 | Pending | Ekoscan BU
Feb | NDTMA 2026 | HIGH | Mining NDT | Vinoth Tharma | Commercial | Identify top 10 Mining NDT target accounts attending — pre-book meetings | 2026-01-30 | Not Started |  | ☐ |  | Cross-ref with Salesforce account list | ACT-010 | Pending | Ekoscan BU
Feb | NDTMA 2026 | HIGH | Mining NDT | Max Aggrey | Commercial | Prepare 3X Composite repair cross-sell kit for NDTMA — embed in every finding conversation | 2026-01-30 | Not Started |  | ☐ |  | 3X = embed at every AMBER/RED finding | ACT-011 | Pending | Ekoscan BU
Feb | NDTMA 2026 | HIGH | Mining NDT | Rick Carlton | Commercial | Post-show: enter all leads in Salesforce, tag Pipeline DA where applicable | 2026-02-22 | Not Started |  | ☐ |  | 48h turnaround rule | ACT-012 | Pending | Ekoscan BU
Mar | IPEIA 2026 | HIGH | All Initiatives | Max Aggrey | Commercial | IPEIA prep meeting — align all 6 attendees on initiative messaging + account targets | 2026-02-15 | Not Started |  | ☐ |  | Highest ROI show of the year | ACT-013 | Pending | BU Services
Mar | IPEIA 2026 | HIGH | All Initiatives | Shanny Tremblay | Logistics | Book flights YQB→Calgary for Max, Keith, Tim, Alex, Rick, Marcos | 2025-12-15 | Not Started |  | ☐ |  | Return ~$620/person CAD | ACT-014 | Pending | BU Services
Mar | IPEIA 2026 | HIGH | All Initiatives | Shanny Tremblay | Logistics | Book hotel — Telus Convention Centre area, 4 nights × 6 people | 2025-12-15 | Not Started |  | ☐ |  | ~$260/night | ACT-015 | Pending | BU Services
Mar | IPEIA 2026 | HIGH | All Initiatives | Shanny Tremblay | Logistics | Confirm booth #78 / 10×10 setup — ship displays + all initiative materials | 2026-02-20 | Not Started |  | ☐ |  | INTACT BU via Nucleom — coordinate with Marcos | ACT-016 | Pending | BU Services
Mar | IPEIA 2026 | HIGH | Nuclear/OPG | Olivier Marcotte | Commercial | Pre-schedule meetings with OPG, Bruce Power, and Aecon contacts at IPEIA | 2026-02-20 | Not Started |  | ☐ |  | Nuclear MSA strategy conversations | ACT-017 | Pending | BU Services
Mar | IPEIA 2026 | HIGH | Pipeline DA | Rick Carlton | Commercial | Pipeline DA: target Enbridge, TC Energy, Pembina contacts — confirm attendance | 2026-02-20 | Not Started |  | ☐ |  | IPC Pipeline preview conversations | ACT-018 | Pending | BU Services
Mar | IPEIA 2026 | HIGH | All Initiatives | Max Aggrey | Commercial | Post-show: team debrief + Salesforce entry within 48h — all 5 initiative tags | 2026-03-15 | Not Started |  | ☐ |  | Mandatory — first Sunday PA run captures these | ACT-019 | Pending | BU Services
Mar | AMPP 2026 | HIGH | Pipeline DA | Rick Carlton | Commercial | AMPP prep: 3X Composite + Pipeline DA messaging for corrosion/integrity audience | 2026-02-28 | Not Started |  | ☐ |  | Vincent Ribouleau attending | ACT-020 | Pending | Ekoscan BU
Mar | AMPP 2026 | HIGH | Pipeline DA | Ekoscan BU Logistics | Logistics | Book flights YQB→Houston for Vincent, confirm hotel near George R. Brown | 2025-12-15 | Not Started |  | ☐ |  | Ekoscan BU manages logistics — coordinate only · ~$820 return CAD | ACT-021 | Pending | Ekoscan BU
Mar | AMPP 2026 | HIGH | 3X Composite | Vinoth Tharma | Commercial | Identify storage tank + pipeline operators for 3X repair cross-sell at AMPP | 2026-02-28 | Not Started |  | ☐ |  | Embed 3X in every AMBER/RED finding convo | ACT-022 | Pending | Ekoscan BU
Apr | CNA 2026 | HIGH | Nuclear/OPG | Jon Eustace | Commercial | CNA Ottawa — prepare Nuclear/OPG strategy brief for Olivier + Jon + LP | 2026-03-30 | Not Started |  | ☐ |  | Largest initiative $47.9M — must be strategic | ACT-023 | Pending | BU Services
Apr | CNA 2026 | HIGH | Nuclear/OPG | Shanny Tremblay | Logistics | Book flights YQB→Ottawa for Oli, Jon, LP, Sha (short drive or flight) | 2026-03-01 | Not Started |  | ☐ |  | Ottawa ~4h drive from QC City or direct flight | ACT-024 | Pending | BU Services
Apr | CNA 2026 | HIGH | Nuclear/OPG | Shanny Tremblay | Logistics | Book ARC Hotel Ottawa — 4 nights × 4 people | 2026-03-01 | Not Started |  | ☐ |  | ~$260/night | ACT-025 | Pending | BU Services
Apr | CNA 2026 | HIGH | Nuclear/OPG | Olivier Marcotte | Commercial | Pre-schedule 1:1 meetings with CNA member utilities and OPG procurement contacts | 2026-03-20 | Not Started |  | ☐ |  | Gate decision: OPG MSA — requires CNA relationship | ACT-026 | Pending | BU Services
Apr | CNA 2026 | HIGH | Nuclear/OPG | Louis-Pierre Théberge | Commercial | CGSB certification status update — confirm team qualifications for OPG outage work | 2026-03-30 | Not Started |  | ☐ |  | LP to confirm all certs current | ACT-027 | Pending | BU Services
Apr | Smart Energy Halifax | LOW | Powerline | Alex Cyr | Logistics | Walkin only — confirm attendees Alex, Eric, Vinoth + register badges | 2026-03-30 | Not Started |  | ☐ |  | No booth — networking only | ACT-028 | Pending | BU Services
Apr | Smart Energy Halifax | LOW | Powerline | Vinoth Tharma | Commercial | Identify Hydro One, Emera, Nova Scotia Power contacts attending Halifax | 2026-04-01 | Not Started |  | ☐ |  | Powerline initiative prospecting | ACT-029 | Pending | BU Services
May | T&D Conference | MED | Powerline | Shanny Tremblay | Logistics | Book flights YQB→Chicago for Math + Sha — return ~$680 CAD each | 2026-03-15 | Not Started |  | ☐ |  | Register for T&D conference passes | ACT-030 | Pending | BU Services
May | T&D Conference | MED | Powerline | Mathieu Beauchesne | Commercial | T&D prep: Powerline initiative deck + Hydro One/AltaLink/ATCO target list | 2026-04-15 | Not Started |  | ☐ |  | $10.2M initiative — primary dedicated show | ACT-031 | Pending | BU Services
May | T&D Conference | MED | Powerline | Mathieu Beauchesne | Commercial | Post-show: enter Powerline prospects in Salesforce — tag BU_Initiative__c = Powerline | 2026-05-10 | Not Started |  | ☐ |  |  | ACT-032 | Pending | BU Services
May | CIM Vancouver | MED | Mining NDT | Vinoth Tharma | Logistics | CIM Vancouver — register walkin badges for Vinoth + Max | 2026-04-01 | Not Started |  | ☐ |  | Walkin only — technical paper TBC | ACT-033 | Pending | BU Services
May | CIM Vancouver | MED | Mining NDT | Vinoth Tharma | Commercial | Submit technical paper abstract if deadline not passed — confirm with organizer | 2026-03-01 | Not Started |  | ☐ |  | Speaker slot = credibility boost | ACT-034 | Pending | BU Services
May | CIM Vancouver | MED | Mining NDT | Max Aggrey | Commercial | BC mining target list: Teck, Copper Mountain, Highland Valley — pre-book meetings | 2026-04-15 | Not Started |  | ☐ |  | West coast mining focus | ACT-035 | Pending | BU Services
Jun | ECNDT Verona | HIGH | All Initiatives | Jon Eustace | Commercial | ECNDT prep: coordinate EIG + Nucleom joint messaging and booth strategy | 2026-05-01 | Not Started |  | ☐ |  | Largest EIG NDT presence of the year | ACT-036 | Pending | Joint
Jun | ECNDT Verona | HIGH | All Initiatives | Shanny Tremblay | Logistics | Book flights YQB→Milan/Verona for Xavier, Guillaume, Lucy, Hervé, Fabian | 2026-03-01 | Not Started |  | ☐ |  | Return ~$1,900 CAD each — book early | ACT-037 | Pending | Joint
Jun | ECNDT Verona | HIGH | All Initiatives | Shanny Tremblay | Logistics | Book hotel Verona — 6 nights × 5 people (~$310/night) | 2026-03-01 | Not Started |  | ☐ |  | Book early — Verona fills up for ECNDT | ACT-038 | Pending | Joint
Jun | ECNDT Verona | HIGH | All Initiatives | Shanny Tremblay | Logistics | Ship booth materials (international freight) — allow 3 weeks lead time | 2026-05-25 | Not Started |  | ☐ |  | Consider Pelican carry-on for key displays | ACT-039 | Pending | Joint
Jun | ECNDT Verona | HIGH | Mining NDT | Vinoth Tharma | Commercial | Pre-schedule meetings with European mining + nuclear operators at ECNDT | 2026-05-15 | Not Started |  | ☐ |  | Global account development | ACT-040 | Pending | Joint
Jun | Canadian Mining Expo | MED | Mining NDT | Jon Eustace | Commercial | PURSUE WAITLIST actively — contact organizer re: speaker slot availability | 2026-01-15 | Not Started |  | ☐ |  | Currently on waitlist — speaker = priority entry | ACT-041 | Pending | BU Services
Jun | Canadian Mining Expo | MED | Mining NDT | Shanny Tremblay | Logistics | Book flights YQB→Timmins for Keith + speaker (once confirmed off waitlist) | 2026-04-01 | Not Started |  | ☐ |  | Regional connection via Toronto ~$580 CAD | ACT-042 | Pending | BU Services
Jun | Canadian Mining Expo | MED | Mining NDT | Vinoth Tharma | Commercial | Timmins target accounts: Vale Timmins, Kinross, Pan American Silver | 2026-05-15 | Not Started |  | ☐ |  | Northern Ontario mining corridor | ACT-043 | Pending | BU Services
Jul | API Inspection Summit | HIGH | Pipeline DA | Jon Eustace | Commercial | COORDINATE with Ekoscan BU — combine booth, split cost, unified message | 2026-05-01 | Not Started |  | ☐ |  | Both teams attending separately — consolidate saves ~$12K | ACT-044 | Pending | BU Services
Jul | API Inspection Summit | HIGH | Pipeline DA | Shanny Tremblay | Logistics | Book flights YQB→San Antonio for Keith, Tim, Alex | 2026-05-01 | Not Started |  | ☐ |  | Return ~$880 CAD each | ACT-045 | Pending | BU Services
Jul | API Inspection Summit | HIGH | Pipeline DA | Shanny Tremblay | Logistics | Book hotel — San Antonio convention area, 5 nights | 2026-05-01 | Not Started |  | ☐ |  | ~$310/night premium convention hotel | ACT-046 | Pending | BU Services
Jul | API Inspection Summit | HIGH | Pipeline DA | Rick Carlton | Commercial | API show prep: Pipeline DA + 3X + Base Business target list — US operators | 2026-06-20 | Not Started |  | ☐ |  | Major US pipeline operators in attendance | ACT-047 | Pending | BU Services
Jul | API Inspection Summit | HIGH | Pipeline DA | Rick Carlton | Commercial | Post-show Salesforce entry — all Pipeline DA + 3X opps within 48h | 2026-07-27 | Not Started |  | ☐ |  |  | ACT-048 | Pending | BU Services
Aug | Cigre Paris | MED | Powerline | Mathieu Beauchesne | Logistics | Book flights YQB→Paris CDG for Math +1 — book 6+ months ahead for best rate | 2026-02-15 | Not Started |  | ☐ |  | Return ~$1,850 CAD — book early | ACT-049 | Pending | BU Services
Aug | Cigre Paris | MED | Powerline | Shanny Tremblay | Logistics | Book hotel Paris — 7 nights × 2 people, near Palais des Congrès | 2026-02-15 | Not Started |  | ☐ |  | ~$310/night | ACT-050 | Pending | BU Services
Aug | Cigre Paris | MED | Powerline | Mathieu Beauchesne | Commercial | Cigre prep: T&D / Powerline initiative follow-up from T&D Chicago contacts | 2026-07-30 | Not Started |  | ☐ |  | Global T&D relationships — EIG alignment | ACT-051 | Pending | BU Services
Sep | IPC Pipeline Conf. | HIGH | Pipeline DA | Jon Eustace | Commercial | IPC is Canada's premier pipeline show — confirm Nucleom booth, brief Max + Vinoth | 2026-07-01 | Not Started |  | ☐ |  | $30M initiative — Rick Carlton anchor event | ACT-052 | Pending | BU Services
Sep | IPC Pipeline Conf. | HIGH | Pipeline DA | Shanny Tremblay | Logistics | Book flights YQB→Calgary for Max, Vinoth (or Rick) | 2026-06-01 | Not Started |  | ☐ |  | Return ~$620 CAD | ACT-053 | Pending | BU Services
Sep | IPC Pipeline Conf. | HIGH | Pipeline DA | Shanny Tremblay | Logistics | Book hotel Calgary — BMO Centre area, 6 nights | 2026-06-01 | Not Started |  | ☐ |  | ~$260/night | ACT-054 | Pending | BU Services
Sep | IPC Pipeline Conf. | HIGH | Pipeline DA | Rick Carlton | Commercial | IPC technical paper submission — Pipeline DA data analytics angle | 2026-06-15 | Not Started |  | ☐ |  | Speaker slot = Pipeline DA credibility | ACT-055 | Pending | BU Services
Sep | IPC Pipeline Conf. | HIGH | Pipeline DA | Rick Carlton | Commercial | Post-IPC: update pipeline opportunity pipeline in Salesforce — all new contacts | 2026-09-28 | Not Started |  | ☐ |  |  | ACT-056 | Pending | BU Services
Sep | IPCE Pipeline Expo | HIGH | Pipeline DA | Rick Carlton | Commercial | Coordinate IPC + IPCE back to back — same Calgary trip where possible | 2026-07-01 | Not Started |  | ☐ |  | Back-to-back Calgary shows — maximize trip | ACT-057 | Pending | BU Services
Sep | CEN CAN Expo | MED | Mining NDT | Vinoth Tharma | Logistics | Book flights YQB→Thunder Bay + hotel — 2 nights regional | 2026-07-15 | Not Started |  | ☐ |  | ~$560 return, ~$185/night regional | ACT-058 | Pending | BU Services
Sep | CEN CAN Expo | MED | Mining NDT | Vinoth Tharma | Commercial | Thunder Bay target accounts: Goldcorp/Newmont Musselwhite, Resolute Mining | 2026-08-15 | Not Started |  | ☐ |  | Northwestern Ontario mining | ACT-059 | Pending | BU Services
Oct | ASNT 2026 | HIGH | Mining NDT | Jon Eustace | Commercial | ASNT Columbus — largest NDT show N.America — confirm 400sqft booth strategy | 2026-07-01 | Not Started |  | ☐ |  | $15K+ booth — needs senior sign-off | ACT-060 | Pending | Joint
Oct | ASNT 2026 | HIGH | Mining NDT | Shanny Tremblay | Logistics | Book flights YQB→Columbus for 4 attendees — book by August | 2026-08-01 | Not Started |  | ☐ |  | Return ~$780 CAD each | ACT-061 | Pending | Joint
Oct | [9 empty] | ☐ |  |  |  | Pending | Joint
Oct | ASNT 2026 | HIGH | Mining NDT | Shanny Tremblay | Logistics | Ship booth — allow 3 weeks, 400sqft requires significant freight planning | 2026-09-20 | Not Started |  | ☐ |  | Largest booth of the year — plan carefully | ACT-063 | Pending | Joint
Oct | ASNT 2026 | HIGH | Mining NDT | Vinoth Tharma | Commercial | ASNT attendee list review — pre-book meetings with top 10 mining + nuclear contacts | 2026-09-20 | Not Started |  | ☐ |  |  | ACT-064 | Pending | Joint
Oct | API Storage Tank | MED-H | Pipeline DA | Rick Carlton | Commercial | API Storage Tank — coordinate with Ekoscan if duplicate attendance | 2026-08-01 | Not Started |  | ☐ |  | Check for consolidation opportunity | ACT-065 | Pending | BU Services
Oct | [9 empty] | ☐ |  |  |  | Pending | BU Services
Ongoing | ALL SHOWS | HIGH | All | Éric Carmichael | Admin | Update conference budget actuals monthly — compare to model in Excel tracker | Monthly | Not Started |  | ☐ |  | First Monday of each month | ACT-067 | — | BU Services
Ongoing | ALL SHOWS | HIGH | All | All Attendees | Commercial | Salesforce entry rule: all leads entered within 48h of return, BU_Initiative__c tagged | After each show | Not Started |  | ☐ |  | Non-negotiable — feeds Sunday PA flow | ACT-068 | — | BU Services
Ongoing | ALL SHOWS | HIGH | All | Jon Eustace | Admin | Quarterly conference budget vs actual review with Mathieu (EVP) | Quarterly | Not Started |  | ☐ |  | Q2: Apr 15 · Q3: Jul 15 · Q4: Oct 15 | ACT-069 | — | BU Services
Ongoing | ALL SHOWS | MED | All | Jon Eustace | Commercial | Post-show pipeline review — verify Salesforce capture and follow-up cadence | After each show | Not Started |  | ☐ |  | Commercial Leadership meeting agenda item | ACT-070 | — | BU Services
Ongoing | ALL SHOWS | HIGH | Nuclear/OPG | Jon Eustace | Commercial | NUCLEAR GAP: identify and add one dedicated Nuclear/OPG event (CANDU Owners Group, OPG Supplier Day) | 2026-02-01 | Not Started |  | ☐ |  | $47.9M initiative needs more dedicated coverage | ACT-071 | — | BU Services
Ongoing | ALL SHOWS | HIGH | Powerline | Mathieu Beauchesne | Commercial | POWERLINE GAP: identify one Canadian utility-focused conference to add (CEATI, Hydro One Supplier Forum) | 2026-02-01 | Not Started |  | ☐ |  | $10.2M initiative — only T&D Chicago currently | ACT-072 | — | BU Services
TOTAL ACTIONS: 72 · Complete: 0 of 72 | [8 empty] | 0 | 0 of 72 complete

## Dashboard
CONFERENCE ACTION PLAN — PROGRESS DASHBOARD 2026
STATUS SUMMARY (auto-updates as you mark items complete in Action Tracker)
Total Actions | Not Started | In Progress | Complete | Blocked
64 | 63 | 0 | 0 | 0
0.0% of actions complete
ACTIONS BY OWNER
Owner | Total | Not Started | In Progress | Complete | Blocked | % Done
Jon Eustace | 6 | 6 | 0 | 0 | 0 | 0%
Olivier Marcotte | 2 | 2 | 0 | 0 | 0 | 0%
Vinoth Tharma | 11 | 11 | 0 | 0 | 0 | 0%
Max Aggrey | 4 | 4 | 0 | 0 | 0 | 0%
Rick Carlton | 11 | 11 | 0 | 0 | 0 | 0%
Mathieu Beauchesne | 4 | 4 | 0 | 0 | 0 | 0%
Éric Carmichael | 0 | 0 | 0 | 0 | 0 | 0%
Alex Cyr | 1 | 1 | 0 | 0 | 0 | 0%
Shanny Tremblay | 17 | 17 | 0 | 0 | 0 | BU Services logistics (Nucleom/Nortech staff only). Shanny is NOT responsible for Ekoscan BU shows.
All Attendees | 0 | 0 | 0 | 0 | 0 | 0%
ACTIONS BY MONTH
Month | Total Actions | Complete | % Done | Upcoming Conferences
Jan | 6 | 0 | 0% | PPIM 2026
Feb | 6 | 0 | 0% | NDTMA 2026
Mar | 10 | 0 | 0% | IPEIA · AMPP
Apr | 7 | 0 | 0% | CNA · Smart Energy Halifax
May | 6 | 0 | 0% | T&D · CIM Vancouver
Jun | 8 | 0 | 0% | ECNDT Verona · Canadian Mining Expo
Jul | 5 | 0 | 0% | API Inspection Summit
Aug | 3 | 0 | 0% | Cigre Paris
Sep | 8 | 0 | 0% | IPC Pipeline · IPCE · CEN CAN Expo
Oct | 5 | 0 | 0% | ASNT · API Storage Tank
Ongoing | 0 | 0 | 0% | Year-round standing items

## Year Calendar
BU SERVICES — 2026 CONFERENCE CALENDAR AT A GLANCE
Month | Priority | Conference | Dates | Location | Initiative | # People | BU Attendees | Booth? | Actions Due | Est. Cost | Status | Approval Decision | Jon's Notes / Rationale | Budget Impact (CAD) | Logistics Owner | Responsible Person | Scope Note | Total Actual (CAD)
January | HIGH | PPIM 2026 | Jan 19-22 | Houston TX | Pipeline DA | 3 | Jeff · Anthony · Aaron | ✓ | 6 | 38000 | Not Started | Pending |  | 0 | Ekoscan BU | Ekoscan Logistics Team | Ekoscan manages logistics — Shanny NOT responsible
February | HIGH | NDTMA 2026 | Feb 17-19 | Las Vegas NV | Mining NDT | 5 | Dillon · Jeff · Fred · Guillaume · Anthony | ✓ | 6 | 42000 | Not Started | Pending |  | 0 | Ekoscan BU | Ekoscan Logistics Team | Ekoscan manages logistics — Shanny NOT responsible
March | HIGH | IPEIA 2026 | Mar 10-12 | Calgary AB | All Initiatives | 6 | Max · Keith · Tim · Alex · Rick · Marcos | ✓ | 7 | 55000 | Not Started | Pending |  | 0 | BU Services | Shanny Tremblay | Shanny Tremblay handles all logistics for Nucleom/Nortech staff
| HIGH | AMPP 2026 | Mar 15-19 | Houston TX | Pipeline DA · 3X | 2 | Vincent Ribouleau | ✓ | 3 | 28000 | Not Started | Pending |  | 0 | Ekoscan BU | Ekoscan Logistics Team | Ekoscan manages logistics — Shanny NOT responsible
April | HIGH | CNA 2026 | Apr 28-30 | Ottawa ON | Nuclear/OPG | 4 | Oli · Jon · LP · Sha | — | 5 | 22000 | Not Started | Pending |  | 0 | BU Services | Shanny Tremblay | Shanny Tremblay handles all logistics for Nucleom/Nortech staff
| LOW | Smart Energy Halifax | Apr 14-15 | Halifax NS | Powerline | 3 | Alex · Eric · Vinoth | — | 2 | 8000 | Not Started | Pending |  | 0 | BU Services | Shanny Tremblay | Shanny Tremblay handles all logistics for Nucleom/Nortech staff
May | MED | T&D Conference | May 4-7 | Chicago IL | Powerline | 2 | Math · Sha | — | 3 | 18000 | Not Started | Pending |  | 0 | BU Services | Shanny Tremblay | Shanny Tremblay handles all logistics for Nucleom/Nortech staff
| MED | CIM Vancouver | May 4-6 | Vancouver BC | Mining NDT | 2 | Vinoth · Max | — | 2 | 9000 | Not Started | Pending |  | 0 | BU Services | Shanny Tremblay | Shanny Tremblay handles all logistics for Nucleom/Nortech staff
June | HIGH | ECNDT Verona | Jun 15-19 | Verona Italy | All Initiatives | 5 | Xavier · Guillaume · Lucy · Hervé · Fabian | ✓ | 5 | 72000 | Not Started | Pending |  | 0 | Joint | Ekoscan + Shanny Tremblay | Coordinate between Ekoscan team and Shanny Tremblay
| MED | Canadian Mining Expo | Jun 9-11 | Timmins ON | Mining NDT | 2 | Keith · Speaker | ✓ | 3 | 18000 | Not Started | Pending |  | 0 | BU Services | Shanny Tremblay | Shanny Tremblay handles all logistics for Nucleom/Nortech staff
July | HIGH | API Inspection Summit | Jul 20-23 | San Antonio TX | Pipeline DA · 3X | 3 | Keith · Tim · Alex | ✓ | 5 | 42000 | Not Started | Pending |  | 0 | BU Services | Shanny Tremblay | Shanny Tremblay handles all logistics for Nucleom/Nortech staff
August | MED | Cigre Paris | Aug 23-28 | Paris France | Powerline | 2 | Math +1 | — | 3 | 28000 | Not Started | Pending |  | 0 | BU Services | Shanny Tremblay | Shanny Tremblay handles all logistics for Nucleom/Nortech staff
September | HIGH | IPC Pipeline Conf. | Sep 21-25 | Calgary AB | Pipeline DA | 2 | Max · Vinoth | ✓ | 5 | 32000 | Not Started | Pending |  | 0 | BU Services | Shanny Tremblay | Shanny Tremblay handles all logistics for Nucleom/Nortech staff
| HIGH | IPCE Pipeline Expo | Sep 22-24 | Calgary AB | Pipeline DA | 2 | Vincent Ribouleau | ✓ | 3 | 26000 | Not Started | Pending |  | 0 | BU Services | Shanny Tremblay | Shanny Tremblay handles all logistics for Nucleom/Nortech staff
| MED | CEN CAN Expo | Sep 9-10 | Thunder Bay ON | Mining NDT | 2 | TBD ×2 | ✓ | 2 | 12000 | Not Started | Pending |  | 0 | BU Services | Shanny Tremblay | Shanny Tremblay handles all logistics for Nucleom/Nortech staff
October | HIGH | ASNT 2026 | Oct 12-15 | Columbus OH | Mining NDT | 4 | TBD ×4 | ✓ | 5 | 68000 | Not Started | Pending |  | 0 | Joint | Ekoscan + Shanny Tremblay | Coordinate between Ekoscan team and Shanny Tremblay
| MED-H | API Storage Tank Expo | Oct 19-22 | Austin TX | Pipeline DA · 3X | 2 | Keith · Tim | ✓ | 4 | 36000 | Not Started | Pending |  | 0 | BU Services | Shanny Tremblay | Shanny Tremblay handles all logistics for Nucleom/Nortech staff
November | MED-H | API Insp. Summit (EIG) | Nov TBC | San Antonio TX | Pipeline DA | 2 | TBD — coordinate w/ Ekoscan | ✓ | 4 | 32000 | Not Started | Pending |  | 0 | Ekoscan BU | Ekoscan Logistics Team | Ekoscan manages logistics — Shanny NOT responsible
Ongoing | HIGH | COFREND Lyon | May 19-21 | Lyon France | Base Business | 6 | Guillaume N · Guillaume P + team | ✓ | 4 | 58000 | Not Started | Pending |  | 0 | Ekoscan BU | Ekoscan Logistics Team | Ekoscan manages logistics — Shanny NOT responsible
TOTAL — 19 conferences · 59 person-attendances | [9 empty] | 644000
APPROVED BUDGET | [11 empty] | 0 | [5 empty] | 0
ON HOLD BUDGET | [11 empty] | 0 | [5 empty] | 0
REJECTED BUDGET | [11 empty] | 0 | [5 empty] | 0
PENDING BUDGET | [11 empty] | 644000 | [5 empty] | 0
HOW TO USE: Open the HTML Conference Action Plan portal in Chrome → review each conference card → click ✓ Approve, ⏸ Hold, or ✗ Reject. Click 'Export Approvals' → copy → paste Jon's notes into Col N here. Change Col M dropdown to match decisions. Budget totals update automatically. Conditional formatting shows green/amber/red by status.
★ SHANNY'S JOB: After each BU Services conference → open this file → find the conference row → enter the total actual cost (from invoices) into Col S (Total Actual). Col S is the master cost record for the Command Centre and Jeremy's quarterly review. The detailed cost breakdown (flights/hotels/booth etc.) goes in Action Tracker tab Col J. NOT responsible for: PPIM · NDTMA · AMPP · COFREND · API Insp. Summit (EIG) — these are Ekoscan BU shows.

## Attendee Action Plan
BU SERVICES — 2026 CONFERENCE ATTENDEE ACTION PLAN · LEADS & OPPORTUNITIES
Track every lead, opportunity, and follow-up from every conference. Enter within 48h of return. Mandatory: Salesforce entry + BU_Initiative__c tag for every row. Nucleom/Nortech staff ONLY — Shanny Tremblay coordinates BU Services shows.
Lead Quality: | HOT | WARM | COLD |  | Opp Stage: | Qualifying | Proposing | Negotiating | Won ✓ | Lost ✗
Conference | Dates | Location | Initiative | Attendee (Our Person) | Contact Name (Lead/Prospect) | Title / Company | Lead Source | Lead Quality | Initiative Tag | Opp Created? | Opp Value (CAD est.) | Opp Stage | Follow-up Date | Follow-up Owner | Follow-up Done? | Salesforce Entry | Notes / Context
IPEIA 2026 ⭐ · Mar 10-12 · Calgary AB · All Initiatives · HIGH · Logistics: BU Services
IPEIA 2026 ⭐ | Mar 10-12 | Calgary AB | All Initiatives | Max Aggrey |  |  | IPEIA 2026 ⭐ Booth |  | All Initiatives | TBD |  |  |  | Max Aggrey | Pending | Pending
IPEIA 2026 ⭐ | Mar 10-12 | Calgary AB | All Initiatives | Keith |  |  | IPEIA 2026 ⭐ Booth |  | All Initiatives | TBD |  |  |  | Keith | Pending | Pending
IPEIA 2026 ⭐ | Mar 10-12 | Calgary AB | All Initiatives | Tim |  |  | IPEIA 2026 ⭐ Booth |  | All Initiatives | TBD |  |  |  | Tim | Pending | Pending
IPEIA 2026 ⭐ | Mar 10-12 | Calgary AB | All Initiatives | Alex Cyr |  |  | IPEIA 2026 ⭐ Booth |  | All Initiatives | TBD |  |  |  | Alex Cyr | Pending | Pending
IPEIA 2026 ⭐ | Mar 10-12 | Calgary AB | All Initiatives | Rick Carlton |  |  | IPEIA 2026 ⭐ Booth |  | All Initiatives | TBD |  |  |  | Rick Carlton | Pending | Pending
IPEIA 2026 ⭐ | Mar 10-12 | Calgary AB | All Initiatives | Marcos |  |  | IPEIA 2026 ⭐ Booth |  | All Initiatives | TBD |  |  |  | Marcos | Pending | Pending
↳ Add rows here for additional contacts met at this conference
CNA 2026 · Apr 28-30 · Ottawa ON · Nuclear/OPG · HIGH · Logistics: BU Services
CNA 2026 | Apr 28-30 | Ottawa ON | Nuclear/OPG | Olivier Marcotte |  |  | CNA 2026 Booth |  | Nuclear/OPG | TBD |  |  |  | Olivier Marcotte | Pending | Pending
CNA 2026 | Apr 28-30 | Ottawa ON | Nuclear/OPG | Jon Eustace |  |  | CNA 2026 Booth |  | Nuclear/OPG | TBD |  |  |  | Jon Eustace | Pending | Pending
CNA 2026 | Apr 28-30 | Ottawa ON | Nuclear/OPG | Louis-Pierre Théberge |  |  | CNA 2026 Booth |  | Nuclear/OPG | TBD |  |  |  | Louis-Pierre Théberge | Pending | Pending
CNA 2026 | Apr 28-30 | Ottawa ON | Nuclear/OPG | Shanny Tremblay |  |  | CNA 2026 Booth |  | Nuclear/OPG | TBD |  |  |  | Shanny Tremblay | Pending | Pending
↳ Add rows here for additional contacts met at this conference
T&D Conference · May 4-7 · Chicago IL · Powerline · MED · Logistics: BU Services
T&D Conference | May 4-7 | Chicago IL | Powerline | Mathieu Beauchesne |  |  | T&D Conference Booth |  | Powerline | TBD |  |  |  | Mathieu Beauchesne | Pending | Pending
T&D Conference | May 4-7 | Chicago IL | Powerline | Shanny Tremblay |  |  | T&D Conference Booth |  | Powerline | TBD |  |  |  | Shanny Tremblay | Pending | Pending
↳ Add rows here for additional contacts met at this conference
CIM Vancouver · May 4-6 · Vancouver BC · Mining NDT · MED · Logistics: BU Services
CIM Vancouver | May 4-6 | Vancouver BC | Mining NDT | Vinoth Tharma |  |  | CIM Vancouver Booth |  | Mining NDT | TBD |  |  |  | Vinoth Tharma | Pending | Pending
CIM Vancouver | May 4-6 | Vancouver BC | Mining NDT | Max Aggrey |  |  | CIM Vancouver Booth |  | Mining NDT | TBD |  |  |  | Max Aggrey | Pending | Pending
↳ Add rows here for additional contacts met at this conference
Canadian Mining Expo · Jun 9-11 · Timmins ON · Mining NDT · MED · Logistics: BU Services
Canadian Mining Expo | Jun 9-11 | Timmins ON | Mining NDT | Keith |  |  | Canadian Mining Expo Booth |  | Mining NDT | TBD |  |  |  | Keith | Pending | Pending
Canadian Mining Expo | Jun 9-11 | Timmins ON | Mining NDT | TBD Speaker |  |  | Canadian Mining Expo Booth |  | Mining NDT | TBD |  |  |  | TBD Speaker | Pending | Pending
↳ Add rows here for additional contacts met at this conference
ECNDT Verona · Jun 15-19 · Verona Italy · All Initiatives · HIGH · Logistics: Joint
ECNDT Verona | Jun 15-19 | Verona Italy | All Initiatives | Xavier |  |  | ECNDT Verona Booth |  | All Initiatives | TBD |  |  |  | Xavier | Pending | Pending
ECNDT Verona | Jun 15-19 | Verona Italy | All Initiatives | Guillaume N |  |  | ECNDT Verona Booth |  | All Initiatives | TBD |  |  |  | Guillaume N | Pending | Pending
ECNDT Verona | Jun 15-19 | Verona Italy | All Initiatives | Lucy |  |  | ECNDT Verona Booth |  | All Initiatives | TBD |  |  |  | Lucy | Pending | Pending
ECNDT Verona | Jun 15-19 | Verona Italy | All Initiatives | Hervé |  |  | ECNDT Verona Booth |  | All Initiatives | TBD |  |  |  | Hervé | Pending | Pending
ECNDT Verona | Jun 15-19 | Verona Italy | All Initiatives | Fabian |  |  | ECNDT Verona Booth |  | All Initiatives | TBD |  |  |  | Fabian | Pending | Pending
↳ Add rows here for additional contacts met at this conference
API Inspection Summit · Jul 20-23 · San Antonio TX · Pipeline DA · HIGH · Logistics: BU Services
API Inspection Summit | Jul 20-23 | San Antonio TX | Pipeline DA | Keith |  |  | API Inspection Summit Booth |  | Pipeline DA | TBD |  |  |  | Keith | Pending | Pending
API Inspection Summit | Jul 20-23 | San Antonio TX | Pipeline DA | Tim |  |  | API Inspection Summit Booth |  | Pipeline DA | TBD |  |  |  | Tim | Pending | Pending
API Inspection Summit | Jul 20-23 | San Antonio TX | Pipeline DA | Alex Cyr |  |  | API Inspection Summit Booth |  | Pipeline DA | TBD |  |  |  | Alex Cyr | Pending | Pending
↳ Add rows here for additional contacts met at this conference
Cigre Paris · Aug 23-28 · Paris France · Powerline · MED · Logistics: BU Services
Cigre Paris | Aug 23-28 | Paris France | Powerline | Mathieu Beauchesne |  |  | Cigre Paris Booth |  | Powerline | TBD |  |  |  | Mathieu Beauchesne | Pending | Pending
Cigre Paris | Aug 23-28 | Paris France | Powerline | TBD |  |  | Cigre Paris Booth |  | Powerline | TBD |  |  |  | TBD | Pending | Pending
↳ Add rows here for additional contacts met at this conference
CEN CAN Expo · Sep 9-10 · Thunder Bay ON · Mining NDT · MED · Logistics: BU Services
CEN CAN Expo | Sep 9-10 | Thunder Bay ON | Mining NDT | Vinoth Tharma |  |  | CEN CAN Expo Booth |  | Mining NDT | TBD |  |  |  | Vinoth Tharma | Pending | Pending
CEN CAN Expo | Sep 9-10 | Thunder Bay ON | Mining NDT | TBD |  |  | CEN CAN Expo Booth |  | Mining NDT | TBD |  |  |  | TBD | Pending | Pending
↳ Add rows here for additional contacts met at this conference
IPC Pipeline Conf. · Sep 21-25 · Calgary AB · Pipeline DA · HIGH · Logistics: BU Services
IPC Pipeline Conf. | Sep 21-25 | Calgary AB | Pipeline DA | Max Aggrey |  |  | IPC Pipeline Conf. Booth |  | Pipeline DA | TBD |  |  |  | Max Aggrey | Pending | Pending
IPC Pipeline Conf. | Sep 21-25 | Calgary AB | Pipeline DA | Vinoth Tharma |  |  | IPC Pipeline Conf. Booth |  | Pipeline DA | TBD |  |  |  | Vinoth Tharma | Pending | Pending
↳ Add rows here for additional contacts met at this conference
IPCE Pipeline Expo · Sep 22-24 · Calgary AB · Pipeline DA · HIGH · Logistics: BU Services
IPCE Pipeline Expo | Sep 22-24 | Calgary AB | Pipeline DA | Rick Carlton |  |  | IPCE Pipeline Expo Booth |  | Pipeline DA | TBD |  |  |  | Rick Carlton | Pending | Pending
↳ Add rows here for additional contacts met at this conference
ASNT 2026 · Oct 12-15 · Columbus OH · Mining NDT · HIGH · Logistics: Joint
ASNT 2026 | Oct 12-15 | Columbus OH | Mining NDT | TBD ×4 |  |  | ASNT 2026 Booth |  | Mining NDT | TBD |  |  |  | TBD ×4 | Pending | Pending
↳ Add rows here for additional contacts met at this conference
API Storage Tank Expo · Oct 19-22 · Austin TX · Pipeline DA · MED-H · Logistics: BU Services
API Storage Tank Expo | Oct 19-22 | Austin TX | Pipeline DA | Keith |  |  | API Storage Tank Expo Booth |  | Pipeline DA | TBD |  |  |  | Keith | Pending | Pending
API Storage Tank Expo | Oct 19-22 | Austin TX | Pipeline DA | Tim |  |  | API Storage Tank Expo Booth |  | Pipeline DA | TBD |  |  |  | Tim | Pending | Pending
↳ Add rows here for additional contacts met at this conference
TOTALS (rows 7–79) · All conferences combined | [10 empty] | 0 | 0 opps created · 0 hot leads · 0 SF entries done